## Basic Gantt Chart
SOFTWARE ENGINEERING GANTT CHART
* = an automatically calculated cell
| TASK NAME | START DATE | END DATE | START ON DAY* | DURATION* (WORK DAYS) | NOTES | WEEK1 | WEEK2 | WEEK3 | WEEK4 | WEEK5 | WEEK6 | WEEK6 | WEEK7 | WEEK8 | WEEK9 | WEEK10
PLANNING
| Brainstorming | 2019-10-01 | 2019-10-02 | 0 | 2 | ALL
| Risk Analysis | 2019-10-03 | 2019-10-05 |  |  | ALL
| Feasibility Study | 2019-10-07 | 2019-10-10 | 6 | 4 | ALL
| Milestone: System Request | 2019-10-11 | 2019-10-13 | 10 | 3 | ALL
COMMUNICATION |  |  |  |  | 1
| Conduct Interviews | 2019-10-24 | 2019-10-27 | 23 | 4 | JAHNAE
| Distribute Surveys | 2019-10-24 | 2019-10-27 |  |  | SARA
| Collect and Analyze Results | 2019-10-28 | 2019-10-29 | 27 | 2 | RUSSELL
| Milestone: Requirements fully outlined | 2019-10-29 | 2019-10-29 | 28 | 1 | ALL
MODELING |  |  |  |  | 1
| Analyzed requirements | 2019-11-01 | 2019-11-01 | 31 | 1 | JAHNAE
| Generated Use Case and Class Diagram | 2019-11-02 | 2019-11-02 | 32 | 1 | SARA
| Generated Sequence and Activity Diagram |  |  |  |  | RUSSELL
| Milestone: UML Diagrams Completed | 2019-11-03 | 2019-11-14 | 33 | 12 | ALL
CONSTRUCTION |  |  |  |  | 1
| Coding | 2019-11-15 | 2019-12-05 | 45 | 21 | ALL
TESTING
| White Box | 2019-12-06 | 2019-12-06 | 66 | 1 | JAHNAE
| Black Box | 2019-12-07 | 2019-12-07 | 67 | 1 | SARA
| Acceptance Testing | 2019-12-08 | 2019-12-08 | 68 | 1 | RUSSELL
Formulas:
DURATION* (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1